## PRODUCT BACKLOG
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
1 | 1 | 1 | User Login | MUST HAVE | 1 | Group A | 3- Completed
|  | 2 | Access Master Billers | MUST HAVE | 2 | Group B | 3- Completed
|  | 3 | Bank manager: Create Bills | MUST HAVE | 3 | Group A | 3- Completed
|  | 4 | Account holder: Create Registered Billers (Auto Pay) | MUST HAVE | 3 | Group B | 3- Completed
|  | 5 | Account holder: View Registered Billers | MUST HAVE | 3 | Group B | 3- Completed
|  | 6 | Account holder: Delete Registered Billers | MUST HAVE | 3 | Group B | 3- Completed
|  | 7 | Account holder: View Bills/Scheduled Payments (Due Date) | MUST HAVE | 3 | Group A | 3- Completed
|  | 8 | Account holder: Manual Payment (Override Auto Pay) | MUST HAVE | 3 | Group A | 3- Completed
|  | 9 | Account holder: View/Export Past payments (date range / biller) (csv) | MUST HAVE | 3 | Group C | 3- Completed
|  | 10 | Auto Pay (Scheduler) (Auto Pay - true?, limit, due date, status) | MUST HAVE | 2 | Group C | 2- In Progress
|  | 10 | E-mail Provision: (3), (8) | MUST HAVE | 2 | Group C | 3- Completed
Group A - Prem Chhabria, Pranay Shridhar, Sumit Raut, Swapnil Ghule
Group B - Anuj Kotarkar, Nishtha Sehgal
Group C - Rutuja More, Sravya Oruganti, Vaishnavi Deokate

## SPRINT-1 BACKLOG
SPRINT 1 - BACKLOG
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Assiginee | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2
[8 empty] | 29.5 | 29 | 0
US 1 | T1 | Managing the login source code with Git & publishing final build using Maven | 2022-08-23 | 2022-08-24 | Prem, Sumit,Pranay,Swapnil | Build | 3- Completed | 0.5 | 0 | 0
| T2 | Adding validators to user inputs | 2022-08-23 | 2022-08-24 |  | Coding | 3- Completed | 0.5 | 0 | 0
| T3 | Unit testing for validator, service, dao | 2022-08-23 | 2022-08-24 |  | Unit Test | 3- Completed | 1 | 0 | 0
US 2 | T1 | Managing master billers source code with Git & publishing final build using Maven | 2022-08-23 | 2022-08-23 | Anuj, Nishtha | Build | 3- Completed | 0.5 | 1 | 0
| T2 | Creating DAO,Service and API | 2022-08-23 | 2022-08-23 |  | Coding | 3- Completed | 0.5 | 2 | 0
| T3 | Testing of Individual functions | 2022-08-23 | 2022-08-23 |  | Unit Test | 3- Completed | 1 | 0.5 | 0
US 3 | T1 | Managing bills source code with Git & publishing final build using Maven | 2022-08-23 | 2022-08-24 | Prem, Sumit,Pranay,Swapnil | Build | 3- Completed | 0.5 | 0 | 0
| T2 | Creating DAO,Service and API | 2022-08-23 | 2022-08-24 |  | Coding | 3- Completed | 1 | 0 | 0
| T3 | Testing of Individual functions | 2022-08-23 | 2022-08-24 |  | Unit Test | 3- Completed | 0.5 | 0 | 0
US 4 | T1 | Managing create registered bills source code with Git & publishing final build using Maven | 2022-08-23 | 2022-08-23 | Anuj, Nishtha | Build | 3- Completed | 1 | 0.5 | 0
| T2 | Creating DAO,Service and API | 2022-08-23 | 2022-08-23 |  | Coding | 3- Completed | 1 | 0.5 | 0
| T3 | Testing of Individual functions | 2022-08-23 | 2022-08-23 |  | Unit Test | 2- In Progress | 1 | 1 | 0
US 5 | T1 | Managing view registered bills source code with Git & publishing final build using Maven | 2022-08-23 | 2022-08-23 | Anuj, Nishtha | Build | 3- Completed | 1 | 2 | 0
| T2 | Creating DAO,Service and API | 2022-08-23 | 2022-08-23 |  | Coding | 3- Completed | 1 | 2 | 0
| T3 | Testing of Individual functions | 2022-08-23 | 2022-08-23 |  | Unit Test | 3- Completed | 1 | 1 | 0
US 6 | T1 | Managing delete registered bills source code with Git & publishing final build using Maven | 2022-08-23 | 2022-08-23 | Anuj, Nishtha | Build | 3- Completed | 1 | 0 | 0
| T2 | Creating DAO,Service and API | 2022-08-23 | 2022-08-23 |  | Coding | 3- Completed | 1 | 0 | 0
| T3 | Testing of Individual functions | 2022-08-23 | 2022-08-23 |  | Unit Test | 3- Completed | 0.5 | 0 | 0
US 7 | T1 | Managing view bills source code with Git & publishing final build using Maven | 2022-08-23 | 2022-08-24 | Prem, Sumit,Pranay,Swapnil | Build | 3- Completed | 1 | 2 | 0
| T2 | Creating DAO,Service and API | 2022-08-23 | 2022-08-24 |  | Coding | 3- Completed | 1 | 1 | 0
| T3 | Testing of Individual functions | 2022-08-23 | 2022-08-24 |  | Unit Test | 3- Completed | 0.5 | 1 | 0
US 8 | T1 | Managing Manual pay source code with Git & publishing final build using Maven | 2022-08-23 | 2022-08-23 | Prem, Sumit,Pranay,Swapnil | Build | 3- Completed | 2 | 2 | 0
| T2 | Creating DAO,Service and API | 2022-08-23 | 2022-08-23 |  | Coding | 3- Completed | 1 | 2 | 0
| T3 | Testing of Individual functions | 2022-08-23 | 2022-08-23 |  | Unit Test | 3- Completed | 1 | 1 | 0
US 9 | T1 | Managing view past bills and export source code with Git & publishing final build using Maven | 2022-08-23 | 2022-08-24 | Rutuja More, Sravya Oruganti, Vaishnavi Deokate | Build | 3- Completed | 0.5 | 1 | 0
| T2 | Creating DAO,Service and API | 2022-08-23 | 2022-08-24 |  | Coding | 3- Completed | 1 | 1 | 0
| T3 | Add CSV export feature | 2022-08-23 | 2022-08-24 |  | Coding | 3- Completed | 0.5 | 1 | 0
| T4 | Testing of Individual functions | 2022-08-23 | 2022-08-24 |  | Unit Test | 3- Completed | 1 | 1 | 0
US 10 | T1 | Managing auto pay source code with MySQL& publishing final build using GIT |  |  | Rutuja, Sravya, Vaishnavi | Build | 1- Not Started | 1 | 1 | 0
| T2 | Configuring Event Scheduler and creating mysql function |  |  |  | Coding | 1- Not Started | 1 | 1 | 0
| T3 | Testing Event Scheduler |  |  |  | Unit Test | 1- Not Started |  |  | 0
| T4 | Testing of Function Constraints |  |  |  | Unit Test | 1- Not Started | 1 | 1 | 0
US10 | T1 | Managing Email source code with Maven & publishing final build using GIT | 2022-08-24 | 2022-08-24 | Rutuja More, Sravya Oruganti, Vaishnavi Deokate | Build | 3- Completed | 1 | 1 | 0
| T2 | Configuring E-mail Credentials | 2022-08-24 | 2022-08-24 |  | Coding | 3- Completed | 1 | 1 | 0
| T3 | Testing Individual Functions | 2022-08-24 | 2022-08-24 |  | Unit Test | 3- Completed | 0.5 | 0.5 | 0

## STAND UP MEETING
Sprint | US ID | Day | Assigned To | Points Discussed | Impediments | Action Taken
1 | US01 | 1 |  | Using different tools discussed the Initial database Schemas and Discussed the points for US1 | NA | NA
| US01 | 1 |  | DTO API using Restmapping | The 500 error code is a generic message that appears when something unexpected happened on the web server and the server can’t offer more specific information | Given multiple attempts atlast we find and resolve the error by searching on the stackoverflow. Solution
| US01 | 1 |  | Creation of MODEL,ENTITY,SERVICE,DAO and then API classes AND Discussed the points about FrontEnd of US 3. | MySQL database connection issue since version was not compatible | Problem solved by adding dependcies and resolved version compatiblility issue
1 | US 04 | 2 |  | Discussed about login provision and it's API | JPA Querry issues for fetching login Id and password of a user | Resolved it using in-built methods of appropriate data types.
| US 10 | 2 |  | Disussed about the Email Provision and its Integration with API | To access database to obtain email while the transaction for saving the new transaction record is persisting without being commited to the db. | Unresolved as of now
| US 07, US 09 | 2 |  | Discussed the need for Inner joins and filters on Tables in the Database | To use filters based on dates and strings in db tables | Resolved it using the Custom query method, wherein the SQL Query was given directly along with all the joins and filters via @Query annotation. Solution
1 | US 03 | 3 |  | Discussed about the test cases for testing Validator, DAO and Service methods of US03 | Not to make permanent changes in database on hitting the DAO class method | Resolved using @Rollback(true)
| US 04 | 3 |  | Discussed about the test cases for testing Validator, DAO and Service methods of US04 | NA | NA
| US05 | 3 |  | Discussed about the test cases for testing Validator, DAO and Service methods of US05 | NA | NA
| US06 | 3 |  | Discussed about the test cases for testing Validator, DAO and Service methods of US06 | NA | NA
| US07 | 3 |  | Discussed about the Mapping used in Entity Class of Advance Booking and design of front End of US-7 | We using ManyToOne mapping instead of OneToMany Mapping.And in front End we face issue regarding the error messages on Book Now/Grab Now Button | We changed the mapping according to design given to us. Searched for how to change a button value and give error messages on every condition.
| US08 | 3 |  | Discussed about the Piping operator used for DateTime or Date Conversion. | Copy Paste from existing source DatePipe Operator | Resolve using Console.log and remove the fifth parseInt because array size is 4 instead of 5
1 | US09 | 4 |  | Discussed about Pagination ,How and what commands need to implement this. | Import Error for Pagination | Remove using Infosys credentials given in angular course
| US10 | 4 |  | Discussed About with what parameters we hit the API And how to implement SELECT ALL/DESELECT ALL | Error faced in SELECT and DESLECT ALL | Created a separate array of Objects which tell about the selected option to cancel
| US02 | 4 |  | Discussed about the JWT errors that we got on day one. | No Such bean found for Load By username and faced an issue in Regex matching | Implement the Load By Username method in service class and Add Regex name in API class
| US07 | 4 |  | Discussed about the test cases of Validator,DAO and Service method of US07 | NA | NA
| US08 | 4 |  | Discussed about the test cases of Validator,DAO and Service method of US08 | NA | NA
| US09 | 4 |  | Discussed about the test cases of Validator,DAO and Service method of US09 | NA | NA
| US10 | 4 |  | Discussed about the test cases of Validator,DAO and Service method of US10 | NA | NA

## Copy of SPRINT-1 BACKLOG (hidden)
SPRINT 1 - BACKLOG
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Assiginee | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
[8 empty] | 95.5 | 72 | 48 | 24 | 0 | 0
US 1 | T1 | Managing the login source code with Git & publishing final build using Maven |  |  |  | Build | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0
| T2 | Adding validators to user inputs |  |  |  | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0
| T3 | Unit testing for validator, service, dao |  |  |  | Unit Test | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0
US 2 | T1 | Managing master billers source code with Git & publishing final build using Maven |  |  |  | Build | 3- Completed | 4 | 2 | 2 | 2 | 0 | 0
| T2 | Managing dependencies for the project. |  |  |  | General | 3- Completed | 4 | 2 | 2 | 2 | 0 | 0
| T3 | Adding JWT authentication |  |  |  | Coding | 3- Completed | 4 | 2 | 2 | 2 | 0 | 0
| T4 | Adding session management |  |  |  | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0
| T5 | Testing token generation and session handling |  |  |  | Unit Test | 3- Completed | 4 | 2 | 2 | 2 | 0 | 0
US 3 | T1 | Creating model and entity classes for Seller Module |  |  |  | Build | 3- Completed | 2.5 | 0 | 0 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0
| T3 | Creating NavBar and Adding Labels to it |  |  |  | Coding | 3- Completed | 2.5 | 0 | 0 | 0 | 0 | 0
| T4 | Creating UI for Coming Soon Product |  |  |  | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0
US 4 | T1 | Creating model and entity classes for Seller Module |  |  |  | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T3 | Creating UI for View Products |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T4 | Creating UI for Coming Soon Product |  |  |  | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
US 5 | T1 | Creating model and entity classes for Seller Module |  |  |  | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T3 | Creating UI for Update Coming Soon Products |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T4 | Creating UI for Coming Soon Product |  |  |  | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
US 6 | T1 | Creating model and entity classes for Seller Module |  |  |  | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T3 | Creating UI for Release Products |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T4 | Creating UI for Coming Soon Product |  |  |  | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
US 7 | T1 | Creating model and entity classes for Customer Module |  |  |  | Build | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T3 | Creating NavBar and Adding Labels to it |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T4 | Creating UI for Create Advance Booking Product |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 0 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 1 | 0 | 0 | 0
US 8 | T1 | Creating model and entity classes for Customer Module |  |  |  | Build | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T3 | Creating UI for Create and View all products |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T4 | Creating UI for View Advance Booking Product |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 0 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 1 | 0 | 0 | 0
US 9 | T1 | Creating model and entity classes for Customer Module |  |  |  | Build | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T3 | Creating UI for Create and View all products |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T4 | Creating UI for Update Advance Booking Product |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
US 10 | T1 | Creating model and entity classes for Customer Module |  |  |  | Build | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T3 | Creating UI for Create and View all products |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T4 | Creating UI for Cancel Advance Booking Product |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 2 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0