## PRODUCT BACKLOG
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
1 | 1 | 1 | User Login | MUST HAVE | 1 |  | 1- Not Started
|  | 2 | Access Master Billers | MUST HAVE
|  | 3 | Bank manager: Create Bills | MUST HAVE | 3 |  | 1- Not Started
|  | 4 | Account holder: Create Registered Billers (Auto Pay) | MUST HAVE | 3 |  | 1- Not Started
|  | 5 | Account holder: View Registered Billers | MUST HAVE | 3 |  | 1- Not Started
|  | 6 | Account holder: Delete Registered Billers | MUST HAVE | 3 |  | 1- Not Started
|  | 7 | Account holder: View Bills/Scheduled Payments (Due Date) | MUST HAVE | 3 |  | 1- Not Started
|  | 8 | Account holder: Manual Payment (Override Auto Pay) | MUST HAVE | 3 |  | 1- Not Started
|  | 9 | Account holder: View/Export Past payments (date range / biller) (csv) | MUST HAVE | 3 |  | 1- Not Started
|  | 10 | Auto Pay (Scheduler) (Auto Pay - true?, limit, due date, status) | MUST HAVE | 3 |  | 1- Not Started
|  | 11 | E-mail Provision: (3), (8) | MUST HAVE

## SPRINT-1 BACKLOG
SPRINT 1 - BACKLOG
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Assiginee | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
[8 empty] | 81.5 | 62 | 41 | 19 | 0 | 0
US 1 | T1 | Managing the login source code with Git & publishing final build using Maven |  |  |  | Build | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0
| T2 | Adding validators to user inputs |  |  |  | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0
| T3 | Unit testing for validator, service, dao |  |  |  | Unit Test | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0
US 2 | T1 | Managing master billers source code with Git & publishing final build using Maven |  |  |  | Build | 2- In Progress | 4 | 2 | 2 | 2 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | General | 2- In Progress | 4 | 2 | 2 | 2 | 0 | 0
| T3 | Testing of Individual functions |  |  |  | Coding | 2- In Progress | 3 | 1 | 1 | 1 | 0 | 0
| T4 | Integrating Back End and Front End |  |  |  | Unit Test | 1- Not Started | 4 | 2 | 2 | 2 | 0 | 0
US 3 | T1 | Managing bills source code with Git & publishing final build using Maven |  |  |  | Build | 3- Completed | 2.5 | 0 | 0 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0
| T3 | Creating UI for Form, |  |  |  | Coding | 3- Completed | 2.5 | 0 | 0 | 0 | 0 | 0
| T4 | Testing of Individual functions |  |  |  | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0
| T5 | Integrating Back End and Front End |  |  |  | Unit Test | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
US 4 | T1 | Managing registered bills source code with Git & publishing final build using Maven |  |  |  | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T3 | Creating UI for Form, |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T4 | Testing of Individual functions |  |  |  | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
| T5 | Integrating Back End and Front End |  |  |  | Unit Test | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
US 5 | T1 | Managing registered bills source code with Git & publishing final build using Maven |  |  |  | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T3 | Creating UI for Form, |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T4 | Testing of Individual functions |  |  |  | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
| T5 | Integrating Back End and Front End |  |  |  | Unit Test | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
US 6 | T1 | Managing registered bills source code with Git & publishing final build using Maven |  |  |  | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T3 | Creating UI for Form, |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T4 | Testing of Individual functions |  |  |  | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
| T5 | Integrating Back End and Front End |  |  |  | Unit Test | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
US 7 | T1 | Managing view bills source code with Git & publishing final build using Maven |  |  |  | Build | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T3 | Creating UI for Table with filters |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T4 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 1 | 1 | 1 | 0 | 0 | 0
| T5 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
US 8 | T1 | Managing Manual pay source code with Git & publishing final build using Maven |  |  |  | Build | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T3 | Add Pay button on US7 UI |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T4 | Add Password Authentication |  |  |  | Coding
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 1 | 1 | 1 | 0 | 0 | 0
US 9 | T1 | Managing view past bills and export source code with Git & publishing final build using Maven |  |  |  | Build | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T3 | Create US7 UI |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T4 | Add CSV export feature |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration
US 10 | T1 | Managing auto pay source code with MySQL& publishing final build using GIT |  |  |  | Build | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T2 | Configuring Event Scheduler and creating mysql function |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T3 | Create toggler in US7 |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T4 | Testing Event Scheduler |  |  |  | Unit Test
| T5 | Testing of Function Constraints |  |  |  | Unit Test | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
US11 | T1 | Managing Email source code with Maven & publishing final build using GIT |  |  |  | Build | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T2 | Configuring E-mail Credentials |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T3 | Testing Individual Functions |  |  |  | Unit Test

## Copy of SPRINT-1 BACKLOG
SPRINT 1 - BACKLOG
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Assiginee | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
[8 empty] | 95.5 | 72 | 48 | 24 | 0 | 0
US 1 | T1 | Managing the login source code with Git & publishing final build using Maven |  |  |  | Build | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0
| T2 | Adding validators to user inputs |  |  |  | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0
| T3 | Unit testing for validator, service, dao |  |  |  | Unit Test | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0
US 2 | T1 | Managing master billers source code with Git & publishing final build using Maven |  |  |  | Build | 3- Completed | 4 | 2 | 2 | 2 | 0 | 0
| T2 | Managing dependencies for the project. |  |  |  | General | 3- Completed | 4 | 2 | 2 | 2 | 0 | 0
| T3 | Adding JWT authentication |  |  |  | Coding | 3- Completed | 4 | 2 | 2 | 2 | 0 | 0
| T4 | Adding session management |  |  |  | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0
| T5 | Testing token generation and session handling |  |  |  | Unit Test | 3- Completed | 4 | 2 | 2 | 2 | 0 | 0
US 3 | T1 | Creating model and entity classes for Seller Module |  |  |  | Build | 3- Completed | 2.5 | 0 | 0 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0
| T3 | Creating NavBar and Adding Labels to it |  |  |  | Coding | 3- Completed | 2.5 | 0 | 0 | 0 | 0 | 0
| T4 | Creating UI for Coming Soon Product |  |  |  | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0
US 4 | T1 | Creating model and entity classes for Seller Module |  |  |  | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T3 | Creating UI for View Products |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T4 | Creating UI for Coming Soon Product |  |  |  | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
US 5 | T1 | Creating model and entity classes for Seller Module |  |  |  | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T3 | Creating UI for Update Coming Soon Products |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T4 | Creating UI for Coming Soon Product |  |  |  | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
US 6 | T1 | Creating model and entity classes for Seller Module |  |  |  | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T3 | Creating UI for Release Products |  |  |  | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0
| T4 | Creating UI for Coming Soon Product |  |  |  | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0
US 7 | T1 | Creating model and entity classes for Customer Module |  |  |  | Build | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T3 | Creating NavBar and Adding Labels to it |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T4 | Creating UI for Create Advance Booking Product |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 0 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 1 | 0 | 0 | 0
US 8 | T1 | Creating model and entity classes for Customer Module |  |  |  | Build | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T3 | Creating UI for Create and View all products |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 0 | 0 | 0
| T4 | Creating UI for View Advance Booking Product |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 0 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 1 | 0 | 0 | 0
US 9 | T1 | Creating model and entity classes for Customer Module |  |  |  | Build | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T3 | Creating UI for Create and View all products |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T4 | Creating UI for Update Advance Booking Product |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
US 10 | T1 | Creating model and entity classes for Customer Module |  |  |  | Build | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T2 | Creating DAO,Service and API |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T3 | Creating UI for Create and View all products |  |  |  | Coding | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T4 | Creating UI for Cancel Advance Booking Product |  |  |  | Coding | 3- Completed | 2 | 2 | 2 | 2 | 0 | 0
| T5 | Testing of Individual functions |  |  |  | Unit Test | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0
| T6 | Integrating Back End and Front End |  |  |  | Integration | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0

## STAND UP MEETING
Sprint | US ID | Day | Assigned To | Points Discussed | Impediments | Action Taken
1 | US01 | 1 |  | Using positional parameters in JPQL, encouraging the use of prepared statement AND Discussed the points for US1 | NA | NA
| US02 | 1 |  | Security API using JWT | Token could not be generated. And we are getting the messsage that you are not authorised to login (Internal Server Error 500) | Given multiple attempts atlast we find and resolve the error by implementing the LoadByUsername function of spring security.
| US03 | 1 |  | Creation of MODEL,ENTITY,SERVICE,DAO and then API classes AND Discussed the points about FrontEnd of US 3. | MySQL Server not supported Hibernate Sequence and mapping of entity class to the tables. | We searched on stackOverflow then we resolve the error by auto_increment the P.K
1 | US 04 | 2 |  | Creation of MODEL,ENTITY,SERVICE,DAO and then API classes AND discussed the points about the Tabular representation of front end of US 4 | NA | NA
| US 05 | 2 |  | Discussed the points about the front end of US 5 AND the how to hit the API twice first to fetch data of unreleased product and then to update the details. | To make the input field from read-only to writable on clicking the update button | Used *ngIf to make the input field hidden until the user clicks the update button
| US 06 | 2 |  | Discussed the points about the front end of US 6 AND how to remove the products from list on clicking the release button | To remove the data from the tabular list on clicking the release button. | Resolved it using the splice method and removed the product from the list
1 | US 03 | 3 |  | Discussed about the test cases for testing Validator, DAO and Service methods of US03 | Not to make permanent changes in database on hitting the DAO class method | Resolved using @Rollback(true)
| US 04 | 3 |  | Discussed about the test cases for testing Validator, DAO and Service methods of US04 | NA | NA
| US05 | 3 |  | Discussed about the test cases for testing Validator, DAO and Service methods of US05 | NA | NA
| US06 | 3 |  | Discussed about the test cases for testing Validator, DAO and Service methods of US06 | NA | NA
| US07 | 3 |  | Discussed about the Mapping used in Entity Class of Advance Booking and design of front End of US-7 | We using ManyToOne mapping instead of OneToMany Mapping.And in front End we face issue regarding the error messages on Book Now/Grab Now Button | We changed the mapping according to design given to us. Searched for how to change a button value and give error messages on every condition.
| US08 | 3 |  | Discussed about the Piping operator used for DateTime or Date Conversion. | Copy Paste from existing source DatePipe Operator | Resolve using Console.log and remove the fifth parseInt because array size is 4 instead of 5
1 | US09 | 4 |  | Discussed about Pagination ,How and what commands need to implement this. | Import Error for Pagination | Remove using Infosys credentials given in angular course
| US10 | 4 |  | Discussed About with what parameters we hit the API And how to implement SELECT ALL/DESELECT ALL | Error faced in SELECT and DESLECT ALL | Created a separate array of Objects which tell about the selected option to cancel
| US02 | 4 |  | Discussed about the JWT errors that we got on day one. | No Such bean found for Load By username and faced an issue in Regex matching | Implement the Load By Username method in service class and Add Regex name in API class
| US07 | 4 |  | Discussed about the test cases of Validator,DAO and Service method of US07 | NA | NA
| US08 | 4 |  | Discussed about the test cases of Validator,DAO and Service method of US08 | NA | NA
| US09 | 4 |  | Discussed about the test cases of Validator,DAO and Service method of US09 | NA | NA
| US10 | 4 |  | Discussed about the test cases of Validator,DAO and Service method of US10 | NA | NA